Unannounced Monthly Centre Visit

Second Level Manager Field Audit — Analysis & Insights

Data source: Google Form responses, 1–23 July 2026 (updated dataset)

73 unannounced visits · 73 centres · 9 Second Level Managers

Prepared for: MIS, Dr. Reddy's Foundation

# 1. Executive Summary

This update refreshes the analysis with 73 unannounced visits recorded between 1 and 23 July 2026 (up from 63 at the last refresh and 41 at first analysis) — the same nine Second Level Managers (SLMs), now covering 73 distinct centres. The underlying pattern from earlier cycles holds: process discipline around alumni follow-up and employer engagement remains the weakest link, aspirant-facing basics remain strong, and a small, consistent set of centres carries real data-veracity risk.

Five headline findings this cycle:

- Alumni Hand-holding is still the single weakest control — 42 of 67 applicable visits (62.7%) flagged “Need Improvement,” though this has improved from 66.7% at the last refresh as more centres catch up on their Contact 1/2/3 cadence.

- Weekly team meeting documentation (54.9%) and Employer Connect (44.3%) remain the next-largest process gaps — Employer Connect specifically has improved noticeably from 60.5% previously, suggesting the push on employer cadence is gaining traction.

- No new data-veracity red flags surfaced in the 10 visits added since the last refresh — the ghost-placement and DOB/age-mismatch findings remain confined to the same six centres identified earlier (five under Amit Chakraborty, one under Gagandeep Singh Sachar), reinforcing that this is a detection-depth issue rather than a spreading problem.

- A new item has entered the weakest-12 list this cycle: “Refer to the activity planner — check if any activities are delayed” now shows 40.4% Need Improvement (19 of 47 applicable visits), driven by a wave of newer visits flagging delayed activities — worth watching next cycle.

- Reporting-depth gaps have shifted, not closed: Phani has grown to the second-highest visit count (13) but the thinnest notes of any high-volume SLM (17 words on average) — the same light-touch-reporting concern previously flagged for Raghavender Rao now applies more visibly to Phani given the higher volume.

Aspirant Interaction remains the strongest section (7.0% Need Improvement), and zero visits across all 73 have reported an aspirant being asked for money for training or placement — the integrity signal from earlier cycles continues to hold at scale.

# 2. Coverage Snapshot

| Metric | Value |
| --- | --- |
| Total visit responses | 73 (up from 63 at last refresh, 41 at first analysis) |
| Unique centres visited | 73 (no repeat visits in the period) |
| Second Level Managers reporting | 9 |
| Date range covered | 1 Jul 2026 – 23 Jul 2026 |
| Checklist items per visit | ~50 items across 4 sections + 4 free-text action logs + 3 reflective questions |
| Programs represented | GROW Youth, HQHCS, CFRSI, Grow-Green-Solar, Accenture/CITI/JPM-partnered Youth batches, and others |

# 3. Section-Wise Compliance Scorecard

| Section | All is Well | Need Improvement | Not Applicable | % Need Improvement |
| --- | --- | --- | --- | --- |
| Data Check (veracity & records) | 407 | 100 | 77 | 19.7% |
| Infra Check | 407 | 106 | 71 | 20.7% |
| Process Check | 939 | 283 | 384 | 23.2% |
| Aspirant Interaction | 639 | 48 | 116 | 7.0% |

All four sections improved slightly versus the last refresh (Process Check 23.2% vs. 29.4%; Data Check 19.7% vs. 23.7%; Infra Check 20.7% vs. 20.5%, essentially flat; Aspirant Interaction 7.0% vs. 8.4%) — a modest but broad-based improvement across the larger sample, though Process Check remains the weakest section by a clear margin.

## 3.1 The 12 Weakest Checklist Items

Ranked by count of “Need Improvement” flags among applicable visits (n = applicable visits).

| Checklist Item | Section | NI / n | % NI |
| --- | --- | --- | --- |
| Verify retention — Alumni Hand-holding Format updated as designed | Data Check | 42 / 67 | 62.7% |
| AH holds a quality weekly team meeting with documented action points | Process Check | 39 / 71 | 54.9% |
| AH regularly meets employers & updates Top 20 Employer format | Process Check | 31 / 70 | 44.3% |
| Any pending infra repairs | Infra Check | 29 / 73 | 39.7% |
| CA’s diary — guided daily by AH during planning days | Process Check | 28 / 68 | 41.2% |
| Aspirant Mock Interview Score Tracker updated in L&D Google Sheet | Process Check | 24 / 69 | 34.8% |
| Any scrap material cleared with support of Admin | Infra Check | 24 / 71 | 33.8% |
| Status of digital infra — PCs, smartboards, tablets, laptops | Infra Check | 24 / 73 | 32.9% |
| AH plans & shares monthly enrolment/placement numbers by the 3rd | Process Check | 21 / 72 | 29.2% |
| AH announces next batch-start date on notice boards by the 3rd | Process Check | 21 / 73 | 28.8% |
| Planning for next batch-start announcement | Process Check | 20 / 72 | 27.8% |
| Refer to the activity planner — check if any activities are delayed (NEW to this list) | Process Check | 19 / 47 | 40.4% |

The list is materially the same as last cycle, still dominated by management-cadence items rather than training-delivery or welfare items. The one new entrant — the activity planner check — is worth flagging to SLMs specifically, since it wasn't a top-12 item previously and its 40.4% rate is now higher than several long-standing entries.

# 4. Deep Dive by Focus Area

## 4.1 Data Veracity

No new red-flag cases were found among the 10 visits added since the last refresh. The six previously identified cases stand unchanged:

Danapur — “11 Aspirant verification initiated... 4 Aspirants found working and 7 doubtful and has not joined the Organization but Placement has been uploaded and shown working for minimum 2 weeks in each case — Disciplinary issue.”

Ghaziabad — “Called 5 Aspirants – 2 Candidates confirmed they had not joined any Organization but shown as Placed is Cogito (346798 & 348902)... Cogito Placement needs Physical visit by SM in next visit.”

Bareilly — “Contacted 4 Aspirants – 1 Parent reverted and shared the candidate left job in 7 days (Anjalee)...”

Plus DOB/age-document mismatches at Dumdum, Kidwainagar, Alambagh, Lucknow-Indiranagar (all Amit Chakraborty) and Vadodara Citi (Gagandeep Singh Sachar). The concentration under a single SLM's verification method is unchanged from the last cycle — this remains the strongest evidence that detection depth, not underlying prevalence, explains why these cases cluster where they do.

- Alumni retention/placement follow-up is still the weakest data-veracity control at 62.7% Need Improvement, though it has improved 4 points since the last refresh.

- Aspirant Registration Forms and staff-attendance/geo-tag issues continue to appear at a similar rate to previous cycles — no material change.

## 4.2 Process Gaps

Process Check remains the weakest section (23.2%, down from 29.4%). The improvement is broad-based rather than concentrated in one item:

- Weekly team meeting documentation improved slightly (54.9% vs. 61.5%) but is still the second-largest gap system-wide.

- Employer Connect shows the largest improvement of any item this cycle (44.3% vs. 60.5% last refresh) — the push on employer-meeting cadence recommended previously appears to be taking hold, though it is still a top-3 gap.

- CA diary review by AHs (41.2%) and Mock Interview tracker maintenance (34.8%) remain persistent, moderate-severity gaps.

- The activity-planner delay check is the one area that got materially worse in relative ranking, newly entering the top 12 — worth a dedicated look next cycle to see if this is a real process slippage or an artifact of more SLMs starting to check this item consistently.

## 4.3 Batch Screening (where applicable)

Screening remains applicable mainly to technical/GROW-Tech programs, consistent with prior cycles.

- Counselling and Screening Forms continue to show a high compliance rate, consistent with the ~93% seen previously.

- Target-group enrolment issues (wrong age/education profile) persist at a similar low-to-moderate rate as before, still worth routine monitoring rather than urgent escalation.

## 4.4 Aspirant Interaction

Still the strongest section (7.0% Need Improvement, improved from 8.4%). Zero visits across all 73 have reported an aspirant being asked for money for training or placement — this clean result has now held across three consecutive data refreshes (41, 63, and 73 visits), which is a meaningful integrity signal in its own right.

- LMS/Skillfy app enrolment and referral-scheme awareness remain the two softer, easily-closed gaps in this section, at rates broadly consistent with prior cycles.

## 4.5 Hostel Visit

Hostel-linked centres remain a minority of the total, so this focus area continues to have a small sample. Findings are consistent with prior cycles — food quality and cleanliness are the recurring issues where hostels exist — and should still be read centre-by-centre rather than as a system trend.

## 4.6 Employer Connect

This is the most improved focus area this cycle: 44.3% Need Improvement, down from 60.5% at the last refresh — a 16-point improvement. It remains a top-3 gap system-wide, so the improvement should be reinforced rather than treated as solved, but the direction is encouraging and suggests the SLM-level push (personally sharing employer leads, holding AHs to a weekly employer-meeting cadence) is working.

## 4.7 Centre Hand-holding

The hand-holding backbone (Alumni Hand-holding, weekly-meeting documentation, CA-diary mentoring, GROW Manual completion) shows a similar pattern to before, with modest improvement across the board:

- Alumni Hand-holding remains the single weakest item system-wide (62.7%, improved from 66.7%).

- GROW Manual Course completion gaps still concentrate in newly joined trainers/CAs and LMS technical issues — an L&D/IT coordination item as before.

- AH/CA hiring delays or resignations were explicitly flagged at 3 centres this cycle (a similar count to before) — continue to treat these as a trigger for a follow-up visit inside 2–3 weeks.

# 5. Insights on Second Level Managers

Updated visit volumes, Need Improvement / Not Applicable rates, and average free-text note length per SLM:

| SLM | Visits | % Need Improvement | % Not Applicable | Avg. words in notes |
| --- | --- | --- | --- | --- |
| S Jakir | 15 | 13.8% | 12.5% | 102 |
| Phani | 13 | 14.5% | 20.9% | 17 |
| Barna | 11 | 21.8% | 21.7% | 47 |
| Amit Chakraborty | 10 | 22.2% | 19.2% | 287 |
| Gagandeep Singh Sachar | 10 | 21.3% | 20.4% | 131 |
| Bhargav Challa | 6 | 23.2% | 20.7% | 124 |
| Mahaboob Basha | 3 | 15.6% | 12.9% | 39 |
| Raghavender Rao | 3 | 9.1% | 10.2% | 18 |
| Sanjay Kumar Tarai | 2 | 32.1% | 17.3% | 388 |

What's changed since the last refresh:

- S Jakir has become the highest-volume SLM (15 visits, up from 2 originally) while maintaining a reasonably thorough note style (102 words average) and one of the lowest Need Improvement rates (13.8%) — currently the strongest combination of volume and depth in the group.

- Phani has grown from 2 visits to 13 — now the second-highest volume — but note depth has not kept pace (17 words average, among the thinnest in the group). This is the clearest new reporting-quality concern this cycle: high volume with light documentation makes it hard to independently verify what's actually being checked at each centre.

- Amit Chakraborty and Sanjay Kumar Tarai remain the two SLMs whose detailed, evidence-heavy notes (287 and 388 words respectively) are the ones actually surfacing hard findings — this pattern is unchanged and still supports rolling their verification method out more broadly.

- Raghavender Rao's profile is unchanged in character (lowest Need Improvement rate, shortest notes, lowest NA usage) — still the profile most in need of an independent quality check on the visit itself rather than just the write-up.

# 6. Recommendations

- Keep pushing the alumni-verification-call standard modelled on Amit Chakraborty's method — it remains the only reliable way this dataset has caught fabricated placements, and no other SLM's notes have surfaced an equivalent finding across three refreshes.

- Reinforce the Employer Connect gains — the 16-point improvement this cycle is real, but 44.3% is still a top-3 gap; keep the weekly employer-meeting cadence and Top 20 Employer format review as a standing SLM checklist item rather than easing off.

- Coach Phani specifically on note depth now that visit volume has scaled to 13 — the same structured template (issue / evidence / owner / date) recommended previously for the group should be applied here as a priority, given the volume-to-depth gap is now the widest of any SLM.

- Investigate the new activity-planner delay flag (40.4%, 19 of 47 visits) next cycle to confirm whether this is a genuine process slippage or simply more consistent checking — either way it now warrants the same attention as the longer-standing top-12 items.

- Continue treating AH/CA vacancy as a red-flag trigger for a follow-up visit inside 2–3 weeks — this pattern held again this cycle.

- Keep Alumni Hand-holding as the top fix-first priority — still the single worst-performing control despite the improvement, and still the Foundation's main defence against inflated placement numbers.

— End of report —